## Burn Chart
Sprint Goals |  |  | Actual Metrics
Sprint | Hours Total | Hours Left | Sprint | Day | Hours Completed | Hours Left
1 | 20 | 4 | 1 | 1 | 14 | 190
2 | 68 | 68 |  | 2 | 2 | 188
3 | 20 | 20 |  | 3
4 | 64 | 64 |  | 4
5 | 32 | 32 |  | 5
6
| Total Hours | 204 |  | 7
|  |  | 2 | 8
9
10
11
12
13
14
|  |  | 3 | 15
16
17
18
19
20
21
|  |  | 4 | 22
23
24
25
26
27
28
|  |  | 5 | 29
30
31
32
33
34
35

## Product Backlog
PRODUCTS | COMPLETED?
User Logs in
User Registers
User views his high scores
User views all time high scores
User plays Minesweeper
Users selects Minesweeper difficulty
User saves game
User views profile
User Edits Profile
User adds picture to profile
User adds friends
User views badges
User view wins, losses, and win loss ratio
user views high score
User plays old game
User search for friends
Admin can delete profiles
Admin can edit profiles
Admin can edit high scores
Admin can add badges
User views rank
Users/other apps can pull high scores through rest api

## Sprint 1
Tasks | Hours Project | Hours Worked | Hours Left | Percent Complete | Day | Team Member | Task | Hours Completed
Login | 4 | 4 | 0 | 100% | 1 | Brydon | Login | 4
Registration | 8 | 8 | 0 | 100% |  | Josh | Registration | 3
Profile | 8 | 4 | 4 | 50% |  | Josh | Registration | 5
[6 empty] | Don | Profile | 2
|  | Total hours: | 20
|  | Total hours left: | 4
[5 empty] | 2 | Josh | Profile | 2
3
4
5
6
7

## Sprint 2
Tasks | Hours Project | Hours Worked | Hours Left | Percent Complete | Day | Team Member | Task | Hours Completed
Game Board | 32 | 0 | 32 | 0% | 1
Scores | 32 | 0 | 32 | 0%
Stats | 4 | 0 | 4 | 0%
|  | Total hours: | 68
|  | Total hours left: | 68
2
3
4
5
6
7

## Sprint 3
Tasks | Hours Project | Hours Worked | Hours Left | Percent Complete | Day | Team Member | Task | Hours Completed
Admin | 8 | 0 | 8 | 0% | 1
Profile Pictures | 8 | 0 | 8 | 0%
User Ranks | 4 | 0 | 4 | 0%
|  | Total hours: | 20
|  | Total hours left: | 20
2
3
4
5
6
7

## Sprint 4
Tasks | Hours Project | Hours Worked | Hours Left | Percent Complete | Day | Team Member | Task | Hours Completed
Badges | 32 | 0 | 32 | 0% | 1
Friend Function | 32 | 0 | 32 | 0%
|  | Total hours: | 64
|  | Total hours left: | 64
2
3
4
5
6
7

## Sprint 5
Tasks | Hours Project | Hours Worked | Hours Left | Percent Complete | Day | Team Member | Task | Hours Completed
Save/Resume Game | 16 | 0 | 16 | 0% | 1
Rest API | 16 | 0 | 16 | 0%
|  | Total hours: | 32
|  | Total hours left: | 32
2
3
4
5
6
7